============================================

GTC-MA PROJECT

Academic Metadata Correction Working Group

=============================================

Founder: Jeremías Oberschelp

Contact email: jeremias.oberschelp@[domain.com]

Start date: February 12, 2026

Version: 1.0

Status: Active

=============================================

INDEX

=============================================

1. Justification

2. Objectives

3. Operational structure

4. Action protocol

5. Inaugural case: Modeling Love Dynamics

6. Documented evidence

7. Next steps

8. Annexes

=============================================

1. JUSTIFICATION

=============================================

Academic metadata has become a graveyard of silent errors.

A single corrupted record replicates across dozens of catalogs,

making knowledge invisible or distorted.

There is no formal citizen channel to report and demand correction.

An individual researcher is ignored. An institutional group is not.

GTC-MA is born to audit, document, and correct serious errors

in the global bibliographic infrastructure.

=============================================

2. OBJECTIVES

=============================================

General:

To establish a replicable, public, and effective mechanism

for detecting and correcting errors in academic bibliographic metadata.

Specific:

1. Document cases of contamination by ISBN, platform, and error type.

2. Intervene systematically with publishers, libraries, and aggregators.

3. Demand correction with deadlines and public verification.

4. Raise awareness about negligence in catalog maintenance.

5. Propose minimum quality control standards for metadata.

=============================================

3. OPERATIONAL STRUCTURE

=============================================

Role                  |                                    Holder               |			 Function

General Coordinator   | Jeremías Oberschelp  | Strategy, spokesperson, follow-up

Metadata Analyst        | To be appointed         | Verifies errors, documents evidence

Technical Writer         | To be appointed         | Prepares letters, reports, templates

Outreach                     | To be appointed         | Academic communication and social media

Library Advisor           | To be appointed         | Normative support

One-person start. Open call for expansion.

=============================================

4. ACTION PROTOCOL

=============================================

Phase 1 – Detection

- Identify ISBN, platform, error type.

- Capture evidence (screenshot, URL, correct reference record).

Phase 2 – Notification

- Send formal letter (template by recipient type).

- Deadline: 10 business days for acknowledgment, 30 for correction.

Phase 3 – Escalation

- No response: resend with copy to superiors.

- Publish case in public repository.

Phase 4 – Verification and closure

- Confirm correction.

- Update case status.

- Acknowledge the entity if diligent.

=============================================

5. INAUGURAL CASE: Modeling Love Dynamics

=============================================

Title:      Modeling Love Dynamics

Authors:    S. Rinaldi, F. Della Rossa, F. Dercole, A. Gragnani, P. Landi

Publisher:  World Scientific, 2015

Correct ISBN (hardcover):   978-981-4696-31-9

Affected ISBN:               978-981-4696-33-3

Platforms with error:        IngentaConnect, Bookwire

Detected error:

- The record with ISBN 978-981-4696-33-3 contains the table of contents

of a completely different book on US-Japan relations.

- On IngentaConnect, searching by ISBN returns 0 results (the book is invisible).

Verified correct records:

- World Scientific Connect: correct

- British Library: correct (ISBN 978-981-4696-31-9)

=============================================

6. DOCUMENTED EVIDENCE

=============================================

Date       		 | Evidence                          		| File

Feb 12, 2026		| Letter to British Library         	| letter-bl.pdf

Feb 12, 2026		| Reply from Sam Ziesler (BL)       	| sam-reply.png

Feb 13, 2026		| Ingenta search: 0 results         	| ingenta-search-0.jpg

Feb 13, 2026		| Letter to Scott Winner (CEO)      	| letter-scott-winner.pdf

Feb 13, 2026		| Sent to info, sales, marketing    	| ingenta-sent.png

All evidence is available in the public repository.

=============================================

7. NEXT STEPS

=============================================

Date        		| Action

Feb 16, 2026		| Resend to Ingenta if no response

Feb 18, 2026		| Publish case in public repository

Feb 20, 2026		| Open call for new members

Feb 23, 2026		| Contact Bookwire

Feb 28, 2026		| First monthly report

=============================================

8. ANNEXES

=============================================

A. Publisher letter template

Subject: Metadata correction – ISBN [XXXXX]

To whom it may concern,

I am reporting a critical metadata error affecting the following title:

- ISBN: [XXXXX]

- Title: [XXXXX]

- Error: [description]

Correct record verified at: [URL]

I request immediate correction and confirmation.

--

Jeremías Oberschelp

GTC-MA

B. Library letter template

Subject: Metadata correction – Catalogue record ISBN [XXXXX]

Dear Cataloguing Team,

The record for ISBN [XXXXX] in your catalogue contains an error: [description].

The correct metadata can be verified at: [URL]

Please correct this record and confirm once done.

--

Jeremías Oberschelp

GTC-MA

C. Useful contacts

Entity            | Contact

------------------|-----------------------------------

British Library   | metadata@bl.uk

World Scientific  | web form (www.worldscientific.com/contactus)

Ingenta (CEO)     | scott.winner@ingenta.com

Ingenta (others)  | info@ingenta.com, sales@ingenta.com, marketing@ingenta.com

Bookwire          | pending investigation

=============================================

SOCIAL MEDIA & REPOSITORIES

=============================================

Mail: buenosaliensjeero@hotmail.com

GitHub:     https://github.com/jeremiasoberschelp/gtc-ma

Repository: Public case files, evidence, templates, and updates

=============================================

SIGNATURE

=============================================

Oberschelp Jeremias

Founder and General Coordinator

Academic Metadata Correction Working Group (GTC-MA)

February 13, 2026